## Slide 1
CISCO SALES CREDITING – AI/ML PROJECT: WEEKLY STATUS REPORT
WSR: 1
Report Duration: Dec 19 – Dec 23, 2022
Objective: Build an AI/ML model which will accept a transaction of any transaction type as input and should predict a Salesrep & Node with a Confidence Score. The AI/ML model should learn and improve based on claims and manual allocations that occur and must reduce cases/ manual interventions
Highlights:
Project Team: Angela, Arun, Kris, Sagar, Lalitha, Nithya, Rakshit, Sathish, Puneet, Pradeep, Riddhi
Sessions conducted so far
  Team introductions
  High level data walk-through
What needs to be achieved by Jan 31, 2023
  Set-up GCP Dev environment with CSDL review & approvals
  Pull data from OTM to GCP
  Set-up GCP BigQuery database
  Set-up GCP Vertex AI components (JupyterLab, Kubeflow pipelines, Deployment environment etc)
  Test availability of complete training data from OTM to GCP BigQuery
  Run initial exploratory Data Analysis
  Start model building activities (Data processing and transformations)
Action items:
Create IDs and environment access for Zensar Team
Provide support to Angela, Lalitha and team for GCP set-up: Document to be shared by Riddhi/Pradeep
Key Dependencies:
Project Status:
Remarks: Zensar team waiting for ID creation and laptops
Create IDs and environment access for Zensar Team
Date: Dec 26, 2022
Show stoppers (if any):
None
Achievements (if any):
Show stoppers:
None

## Slide 2
CISCO SALES CREDITING – AI/ML PROJECT: Minutes of Meeting – 19. 12 . 2022
Attendees and Time: 19th December 2022, 09:00 AM – 10:15 AM PST, WebEx Online
  Zensar: Riddhi Dutta, Pradeep Varanasi
  CISCO: Arun, Angela, Bajaj, Lalitha + 1
Topics Covered:
  Existing approach: The cases are bound with rules (combination of Node, Territory, Sales Rep ID) and a machine learning model is plugged to predict whether a case should be auto processed based on matched rules or sent to PEGA to create manually.
  Existing data flow: The data is processed from OTM (Oracle Territory Management) and fed to KAFKA  Incorta  Machine Learning Model Predictions  KAFKA  Actionable Insights or PEGA
  Existing challenges:
    Change of Sales Rep IDs and other parameters every fiscal year
    Unallocated nodes due to unassigned territories
    High Auto/Manual ratio
  Introduction to the data snapshot, features, primary key (transaction ID and transaction line), expected records in a quarter. (To be continued on 20th December 2022)
Zensar’s Approach/Objective:
  Data cleansing recommendation, Pre-processing, Feature engineering, Exploratory data analysis
  LSTM/Regression/Time-series exploration on the final dataset along with Optimization.
  Reduce the Auto/Manual ratio.

## Slide 3
OTM
KAFKA
GCP
ML/DL
KAFKA
Oracle Territory Management to store the sales data
Stream-processing platform that generates leads every ‘x’ minutes
Google Cloud Platform to trigger the Flask API
Data is inputted to a Machine Learning/Deep Learning model
Stream-processing platform for pushing results to the relevant source
CISCO SALES CREDITING – AI/ML PROJECT: Data Pipeline Architecture (imagined)

## Slide 4
CISCO SALES CREDITING – AI/ML PROJECT: Project Plan
We are here

## Slide 5
Thank you!