## Project Plan
|  |  | 2022-01-02 | 2022-01-09 | 2022-01-16 | 2022-01-23 | 2022-01-30 | 2022-02-06 | 2022-02-13 | 2022-02-20 | 2022-02-27 | 2022-03-06 | 2022-03-13 | 2022-03-20 | 2022-03-27 | 2022-04-03 | 2022-04-10 | 2022-04-17 | 2022-04-24 | 2022-05-01 | 2022-05-08 | 2022-05-15 | 2022-05-22 | 2022-05-29 | 2022-06-05 | 2022-06-12 | 2022-06-19 | 2022-06-26
Scope | Activity | Owner | bar: 2022-01-02 to 2022-06-26
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26
Setup environments | Setup GCP Dev environments with CSDL review & approvals | Zensar/Cisco | bar: 1 to 3
| Setup Kafka stream from OTM to GCP for all transactions and test | Zensar/OTM | bar: 4 to 7
| Setup Kafka stream from GCP to Pega and test | Zensar/Pega | bar: 6 to 7
| Setup Kafka stream from GCP to OneCAT | Zensar/OneCAT | bar: 7 to 8
2.1.0 - Given a transaction of any transaction type is input into Sales Crediting AI Then AI should predict a Salesrep & Node with a Confidence Score And the AI should learn and improve based on claims and manual allocations that occur | Exploratory Data Analysis | Zensar | bar: 4 to 6
| Build and train multiple heuristic and ML models In Dev | Zensar | bar: 6 to 9
| Test models and refine | Zensar | bar: 9 to 11
| Finalize approach and training cycle | Zensar | bar: 11 to 12
| Setup GCP Prod environments with CSDL review & approvals | Zensar/Cisco | bar: 9 to 11
2.1.1 - Given AI decides to create a case for Pega, Then publish the Salesrep, Node, and Confidence Score to Pega | Simulate training, prediction and data transfers in Dev | Zensar/PEGA/OTM | bar: 13 to 14
| Performance Test of Pipeline & model | Zensar | bar: 15 to 16
| Data consumption testing by Pega team | Pega | bar: 15 to 18
2.2.1 - Given a transaction of Deal ID Territory Type is input into Sales Crediting AI Then AI should predict a Salesrep & Node with a Confidence Score. And the AI should learn and improve based on claims and manual allocations that occur | Data consumption testing by OneCAT team | OneCAT team | bar: 17 to 18
| UAT and metrics analysis | Zensar | bar: 19 to 20
| End to End connectivity test in Prod Environment | Zensar | bar: 20
2.2.2 - If the prediction differs from the current Salesrep/Node, then the transaction is flagged is manual. The predicted Salesrep, Node, and Confidence Score are published to the Kafka topic for consumption by Pega. The sames create/delete events apply to Deal ID Territory Types that apply to the other existing types. | Deploy code in Prod and run cycles | Zensar | bar: 21 to 22
| Go Live Phase II - 2.1.0, 2.1.1, 2.2.1,2.2.2 | OTM/Zensar/PEGA/Cisco
-- Cut off Kafka Incorta and switch to GCP
| Accuracy and metrics monitoring | Zensar/Cisco | bar: 23
| Post Production Warranty | Zensar | bar: 23 to 24
3.1.1 - Given a transaction that requires Customer Validation is input into Sales Crediting AI And a record exists for this transaction in the Sales Crediting AI archive. Then make a prediction for SAV ID, Party ID And include a Confidence Score And identify the associated SAV Name & Party Name | Exploratory Data Analysis | Zensar | bar: 13 to 14
| Build and train models In Dev | Zensar | bar: 14 to 16
| Test models and refine | Zensar | bar: 17
3.1.2 - Given a transaction that requires Customer Validation is input into Sales Crediting AI And a record does NOT exist for this transaction in the Sales Crediting AI archive Then make a prediction for SAV ID, Party ID And include a Confidence Score And identify the associated SAV Name & Party Name | Finalize approach and training cycle | Zensar | bar: 18
| Simulate training, prediction and data transfers in Dev | Zensar/OneCAT/OTM | bar: 19
| UAT and metrics analysis | Zensar | bar: 20
| Deploy code in Prod and run cycles | Zensar | bar: 21
| Go Live Phase II - 3.1.1, 3.1.2, 3.1.3 | OTM/Zensar/OneCAT/Cisco
3.1.3 - Given a transaction has a SAV ID and Party ID prediction,Then populate and upload the CV template into OneCAT | Accuracy and metrics monitoring | Zensar/Cisco | bar: 22
| Post Production Warranty | Zensar | bar: 22 to 26